## PnGs
BID NO.: INF-W41/2022/2023 CONSTRUCTION OF BULK WATER SUPPLY IN GROOTPAN, SIAS, LONGDEN GA-RAMASWIKANA (SOUTH CLUSTER) CAPRICORN DISTRICT MUNICIPALITY SCHEDULE OF QUANTITIES SECTION A: PRELIMINARY AND GENERAL
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
| SANS 1200A | SECTION A: PRELIMINARY & GENERAL
A.1 | PS A 8.3 | FIXED-CHARGE ITEMS
A.1.1 | PSA 8.3.1 | Contractual Requirements |  | Sum | 1
A.1.2 | PSA 8.3.2 | Establish Facilities on the Site :
| PSA 8.3.2.1 | Facilities for Engineer
A.1.2.1 |  | a) Furnished Office (PSAB 3.2) |  | Sum | 1
A.1.2.2 |  | b) Nameboards (PS AB 3,2) |  | Sum | 1
A.1.2.3 |  | c) Telephone |  | Sum | 1
A.1.3 | PSA 8.3.2.2 | Facilities for Contractor
A.1.3.1 |  | a) Offices and storage sheds |  | Sum | 1
A.1.3.2 |  | b) Workshops |  | Sum | 1
A.1.3.3 |  | e) Ablution and latrine facilities |  | Sum | 1
A.1.3.4 |  | f) Tools and equipment |  | Sum | 1
A.1.3.5 |  | g) Water supplies, electric power and communications |  | Sum | 1
A.1.3.6 |  | h) Dealing with water (Subclause 5.5) |  | Sum | 1
A.1.3.7 |  | i) Access (Subclause 5.8) |  | Sum | 1
A.1.3.8 |  | j) Plant |  | Sum | 1
A.1.3.9 | PS A 8.3.3 | Other Fixed-Charge Obligations |  | Sum | 1
A.1.3.10 | PSA 8.3.4 | Removal of Site Establishment |  | Sum | 1
A.1.4 | PSA B 8.3.5 | Occupational Health And Safety
A.1.4.1 | PSA B 8.3.5.1 | Contractor’s initial obligations in respect of the Occupation Health and Safety Act and Contractual Regulations |  | P/ Sum | 1 | 108000
A.1.4.2 | PSA B 8.3.5.2 | Occupational, Health and Safety Act |  | % |  | 108000
SUB-TOTAL CARRIED FORWARD
brought forward
A.2 | PS A 8.4 | SCHEDULED TIME RELATED ITEMS
A.2.1 | SANS 1200 AB | Engineer's Office
A.2.1.1 | PSAB 8.2.2(a) | Office buildings |  | Sum | 1
A.2.1.2 | PSAB 8.2.2(b) | Telephone and fax |  | Sum | 1
A.2.1.3 | PSAB 8.2.2(d) | Survey assistance and equipment |  | Sum | 1
A.2.2 | PSA 8.4.2.2 | Facilities for Contractor
A.2.2.1 |  | a) Offices and storage sheds |  | Month | 12
A.2.2.2 |  | b) Workshops |  | Month | 12
A.2.2.3 |  | e) Ablution and latrine facilities |  | Month | 12
A.2.2.4 |  | f) Tools and equipment |  | Month | 12
A.2.2.5 |  | g) Water supplies, electric power and communications |  | Month | 12
A.2.2.6 |  | h) Dealing with water (Subclause 5.5) |  | Month | 12
A.2.2.7 |  | i) Access (Subclause 5.8) |  | Month | 12
A.2.2.8 |  | j) Plant |  | Month | 12
A.2.2.9 | PSA 8.4.3 | Supervision for Duration of Construction |  | Month | 12
A.2.2.10 | PSA 8.4.4 | Company and Head Office Overhead Cost/s for the Duration of the Contract |  | Month | 12
SUB-TOTAL CARRIED FORWARD
brought forward
A.3 | PS A 8.5 | SUMS STATED PROVISIONALLY BY ENGINEER
A.3.1 |  | (a)1 Community Liaison Officer |  | P/Sum | 1 | 96000
A.3.2 |  | (a) 2 PSC Meetings Attendance |  | P/Sum | 1 | 36000
A.3.3 |  | (a)3 Overheads, charges and profit on (a)1 & 2 above |  | % |  | 132000
A.3.4 |  | (b)1 Training |  | P/Sum | 1 | 100000
A.3.5 |  | (b)2 Overheads, changes and profit on (b)1 above |  | % |  | 100000
A.3.6 |  | (c)1 Relocation and repair to existing Services |  | P/Sum | 1 | 50000
A.3.7 |  | (c)2 Overheads, changes and profit on c)1 above |  | % |  | 50000
| 8.8.5 | Land Survey Act
A.3.8 |  | d) 1 Search for and record tri- gonometrical survey beacons, bench marks and plot and protect boundary pegs, and expose on completion of Works |  | P/Sum | 1 | 60000
A.3.9 |  | d)2 Overheads, charges and profit on item d)1 above. |  | % |  | 60000
A.3.10 |  | Electrical and Mechanical Equipment
Additional at:
A.3.11 |  | e)1 Mechanical and Electrical work to be completed by Sub-contractor including applications to Eskom for service connections and installations. |  | P/Sum | 1 | 500000
A.3.12 |  | e)2 Overheads, charges and profit on item e)1 above. |  | % |  | 500000
A.3.13 |  | f)1 Electrical work at boreholes to be completed by Sub-contractor |  | P/Sum | 1 | 500000
A.3.14 |  | f)2 Overheads, charges and profit on item f)1 above. |  | % |  | 500000
SUB-TOTAL CARRIED FORWARD
brought forward
A.3.15 |  | g)1 Additional specialist studies |  | P/Sum | 1 | 80000
A.3.16 |  | g)2 Overheads, charges and profit on item g)1 above. |  | % |  | 80000
Material Testing
A.3.17 |  | h)1 Acceptance testing of material and workmanship called for by the Engineer at a nominated laboratory. |  | P/Sum | 1 | 80000
A.3.18 |  | h)2 Overheads, charges and profit on item h)1 above. |  | % |  | 80000
A.3.19 |  | i)1 Allowance for appointment of a Supervisory Control and Data Aquisation contractor |  | P/Sum | 1 | 500000
A.3.20 |  | i)2 Overheads, charges and profit on item i)1 above. |  | % |  | 500000
A.3.21 |  | j)1 Allowance for siting and drilling of an additional 3 boreholes |  | P/Sum | 1 | 0
A.3.22 |  | j)2 Overheads, charges and profit on item j)1 above. |  | % |  | 0
A.4 | PS A 8.8 | TEMPORARY WORKS
A.4.1 | PS A 8.8.2 | Accommodation Of Traffic |  | Sum | 1 | 80000
TOTAL CARRIED FORWARD TO SUMMARY

## Site Clearance
BID NO.: INF-W41/2022/2023 CONSTRUCTION OF BULK WATER SUPPLY IN GROOTPAN, SIAS, LONGDEN GA-RAMASWIKANA (SOUTH CLUSTER) CAPRICORN DISTRICT MUNICIPALITY SCHEDULE OF QUANTITIES SECTION B: SITE CLEARANCE
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SECTION B: SITE CLEARANCE
B.1 |  | SITE CLEARANCE
B.1.1 | 8.2.1 and PSC 8.2.1 | Clear and grub Site for:
B.1.1.1 |  | Pipeline routes |  | m | 11000
B.1.1.2 |  | Pipeline routes | LI | m | 6000
B.1.1.3 |  | Areas for Elevated Tanks (PS C 5.1) | LI | m² | 0
B.1.1.4 |  | Area for Boreholes (PS C 5.1) | LI | m² | 480
B.1.2 | PS C 8.2.2 | Remove and grub large trees and tree stumps of girth :
B.1.2.1 |  | a) over 1 m and up to and including 2 m | LI | No. | 50
B.1.2.2 |  | b) over 2 m and up to and including 3 m | LI | No. | 30
B.1.3 |  | Demolish and remove existing structures, reinstate or remove to dump site as per project specification:
B.1.3.1 | PSC 8.2.5 | Take down existing fences where directed by the Engineer | LI | m | 400
B.1.3.2 | 8.2.7 | Removal of existing pipelines | LI | m | 2230
TOTAL CARRIED FORWARD TO SUMMARY

## Earthworks
BID NO.: INF-W41/2022/2023 CONSTRUCTION OF BULK WATER SUPPLY IN GROOTPAN, SIAS, LONGDEN GA-RAMASWIKANA (SOUTH CLUSTER) CAPRICORN DISTRICT MUNICIPALITY SCHEDULE OF QUANTITIES SECTION C: EARTHWORKS
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
| SANS 1200D | SECTION C: EARTHWORKS
C.1 |  | EXCAVATION
C.1.1 | 8.3.1.2 | Remove topsoil to nominal depth 150mm, stockpile and maintain
C.1.1.1 |  | (1) Along pipeline routes |  | m2 | 39000
C.1.1.2 |  | (2) At elevated taks sites |  | m2 | 0
C.1.2 | 8.3.4 | Cut to fill |  | m3 | 20
C.1.3 |  | Compact to 90% of modified AASHTO maximum density (in layers of 150mm) |  | m3 | 40
C.1.4 |  | Selected layer G8 material compacted to 93 % of modified AASHTO maximum density (in layers of 150mm) |  | m3 | 40
C.1.5 |  | Selected layer G7 material compacted to 93 % of modified AASHTO maximum density (in layers of 150mm) |  | m3 | 40
C.1.6 | 8.3.7 | Cut to spoil
C.1.7 |  | In all materials other than hard excavation |  | m3 | 120
C.2 | PSDB 8.3.3 | EXCAVATION ANCILLARIES
C.2.1 | PSDB 8.3.3.1 | Make up deficiency in backfill material
C.2.1.1 |  | a) from other necessary excavations on site |  | m3 | 300
C.2.1.2 |  | c) by importation from commercial or off-site sources selected by the Contractor |  | m3 | 300
SUB-TOTAL CARRIED FORWARD
brought forward
C.2.2 | PSDB 8.3.5 | Existing Services
| PSDB 8.3.5(a) | Existing services that intersect or adjoin pipe trench excavations
C.2.2.1 |  | i) Electric cables | LI | No. | 30
C.2.2.2 |  | ii) Telephone/Eskom cables | LI | No. | 30
C.2.2.3 |  | iii) Water main up to 300mm diameter | LI | No. | 20
C.2.2.4 |  | iv) Water main exceeding 300mm but not exceeding 600mm diameter | LI | No. | 20
C.2.2.5 |  | v) Overhead cables | LI | No. | 20
| PSDB 8.3.5(b) | b) Services that adjoin a trench
C.2.2.6 |  | i) Electric cables | LI | No. | 30
C.2.2.7 |  | ii) Telephone/Eskom cables | LI | No. | 1000
C.2.2.8 |  | iii) Water main up to 300mm diameter | LI | No. | 500
C.2.2.9 |  | iv) Water main exceeding 300mm but not exceeding 600mm diameter | LI | No. | 20
C.2.2.10 |  | v) Overhead cables | LI | No. | 1000
C.2.2.11 | 8.3.8.1c | Hand excavation for the detection, exposure and protection of existing services | LI | m3 | 500
C.2.3 | PS DB 8.3.6 | Finishing
| PS DB 8.3.6.1 | Reinstate road surfaces complete with all courses
C.2.3.1 |  | a) Gravel | LI | m2 | 500
C.2.3.2 | 8.3.10 | Topsoiling |  | m³ | 5850
SUB-TOTAL CARRIED FORWARD
brought forward
C.2.4 | 8.3.4 | Cut to fill
C.2.4.1 |  | Compact to 90% of modified AASHTO maximum density (in layers of 150mm) |  | m3 | 1500
C.2.4.2 |  | Selected layer G8 material compacted to 93 % of modified AASHTO maximum density (in layers of 150mm) |  | m3 | 350
C.2.4.3 |  | Selected layer G7 material compacted to 93 % of modified AASHTO maximum density (in layers of 150mm) |  | m3 | 80
C.2.5 | 8.3.7 | Cut to spoil
C.2.5.1 |  | In all materials other than hard excavation |  | m3 | 210
C.2.6 |  | Removal of temporay road
C.2.6.1 | 8.3.7 a) | Cut to spoil temporary road materials |  | m3 | 200
TOTAL CARRIED FORWARD TO SUMMARY
|  |  |  | 270000 | 1.1 | 297000

## Civil Works-Pipe Work
BID NO.: INF-W41/2022/2023 CONSTRUCTION OF BULK WATER SUPPLY IN GROOTPAN, SIAS, LONGDEN GA-RAMASWIKANA (SOUTH CLUSTER) CAPRICORN DISTRICT MUNICIPALITY SCHEDULE OF QUANTITIES SECTION D: CIVIL WORKS - PIPE WORK
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
| SANS 1200LE | SECTION D: CIVIL WORKS PIPEWORK
D.1 |  | PIPE WORK
D.1.1 | PSDB 8.3.2 | Excavation
| PSDB 8.3.2(a) | Excavate in all materials for trenches backfill, compact, and dispose of surplus/unsuitable material, for pipes: up to 200 mm in diameter for total trench depth: Exceeding but not exceeding
D.1.1.1 |  | 0,0 m 1,0 m |  | m | 150
D.1.1.2 |  | 1,0 m 2,0 m |  | m | 15000
D.1.1.3 |  | 2,0 m 3,0 m |  | m | 500
| PSDB 8.3.2(a) | Excavate in all materials for trenches backfill, compact, and dispose of surplus/unsuitable material, for pipes: over 200 mm up to 400 mm in diameter for total trench depth: Exceeding but not exceeding
D.1.1.4 |  | 0,0 m 1,0 m |  | m | 0
D.1.1.5 |  | 1,0 m 2,0 m |  | m | 0
D.1.1.6 |  | 2,0 m 3,0 m |  | m | 0
D.1.1.7 |  | 3,0 m 4,0 m |  | m | 0
| PSDB 8.3.2(a) | Excavate in all materials for trenches backfill, compact, and dispose of surplus/unsuitable material, for pipes: over 400 mm up to 600 mm in diameter for total trench depth: Exceeding but not exceeding
D.1.1.8 |  | 0,0 m 1,0 m |  | m | 0
D.1.1.9 |  | 1,0 m 2,0 m |  | m | 0
D.1.1.10 |  | 2,0 m 3,0 m |  | m | 0
D.1.1.11 |  | 3,0 m 4,0 m |  | m | 0
SUB-TOTAL CARRIED FORWARD
brought forward
| PSDB 8.3.2(b) | Extra-over item (a) above for:
D.1.1.12 |  | 1. Intermediate Excavations |  | m³ | 14000
D.1.1.13 |  | 2. Hard Excavations |  | m³ | 8500
D.1.1.14 |  | 3. Rock Excavations |  | m³ | 1500
D.1.1.15 | 8.3.3 | 4) Boulder Excavation |  | m³ | 500
D.1.1.16 |  | 3. Hand excavation and backfill where ordered by the engineer | LI | m³ | 100
D.1.1.17 |  | 4. Soil Crete backfilling where directed by the engineer | LI | m³ | 50
D.1.1.18 | PSDB 8.3.2(c) | Excavate and dispose of unsuitable material from trench bottom (provisional) | LI | m³ | 500
D.1.2 | PSDB 8.3.3 | EXCAVATION ANCILLARIES
| PSDB 8.3.3.1 | Make up deficiency in backfill material
D.1.2.1 |  | a) from other necessary excavations on site |  | m³ | 200
D.1.2.2 |  | b) by importation from-designated borrow pits |  | m³ | 300
D.1.2.3 |  | c) by importation from commercial or off-site sources selected by the Contractor |  | m³ | 1500
D.1.2.4 | PSDB8.3.3.2 | Opening up and closing down of designated borrow pits | LI | Sum | 1
TOTAL CARRIED FORWARD TO SUMMARY
|  |  |  | 270000 | 1.1 | 297000

## Bulk Pipelines
BID NO.: INF-W41/2022/2023 CONSTRUCTION OF BULK WATER SUPPLY IN GROOTPAN, SIAS, LONGDEN GA-RAMASWIKANA (SOUTH CLUSTER) CAPRICORN DISTRICT MUNICIPALITY SCHEDULE OF QUANTITIES SECTION E: BULK PIPELINES
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
| SANS 1200L | SECTION E: MEDIUM PRESSURE PIPELINES
E.1 |  | BULK PIPELINES
E.1.1 | PSL 8.2.1 | Supply, Lay and Bed Pipes complete with couplings
| PSL 8.2.1.1 | Supply, Lay, Joining, Bedding, Testing and Disinfection of uPVC Class 12 Pipes with the following diameters:
E.1.1.1 |  | 110 mm | LI | m | 579
E.1.1.2 |  | 160 mm | LI | m | 2560
E.1.1.3 | PSL 8.2.2 | Extra-over 8.2.1 for the Supplying, Laying, Bedding and Testing of Specials Complete with Couplings
90° elbows:
E.1.1.4 |  | 110 mm | LI | No | 2
E.1.1.5 |  | 160 mm | LI | No | 2
45° elbows:
E.1.1.6 |  | 110 mm | LI | No | 2
E.1.1.7 |  | 160 mm | LI | No | 2
22,5° elbows:
E.1.1.8 |  | 110 mm | LI | No | 1
E.1.1.9 |  | 160 mm | LI | No | 1
11,25° elbows:
E.1.1.10 |  | 110 mm | LI | No | 1
E.1.1.11 |  | 160 mm | LI | No | 1
Tees:
E.1.1.12 |  | 110 mm x 110 mm | LI | No | 1
SUB-TOTAL CARRIED FORWARD
brought forward
Reducers:
E.1.1.13 |  | 160 x 110mm | LI | No | 1
E.1.1.14 |  | 110 x 90mm | LI | No | 1
E.1.1.15 | PSL 8.2.3 | Extra-over 8.2.1 for the Supply, Fixing, Bedding and Testing of Valves. Supply and install on conrete support, join, including cut pipes where necessary, test, cap top. Resilient seal valve, anti clockwise closing, waterworks double flanged, including vj coupling and denso tape.
| PSL 8.2.13 | Supply and installation of pre-cast valve chambers (complete as per drawing W74-20/21-BLK-W-D005)
E.1.1.16 |  | 25 mm Air valve | LI | No | 10
E.1.1.17 |  | 50 mm Air valve | LI | No | 1
Supply and installation of pre-cast scour valves (see drawing W74-20/21-BLK-W-D007)
E.1.1.18 |  | 75 mm Scour valve | LI | No | 4
|  | 110 mm Scour valve | LI | No | 1
|  | 160 mm Scour valve | LI | No | 1
| PS L 3.10.1 | Supply and installation of pre-cast gate valves (see drawing W74-20/21-BLK-W-D008)
E.1.1.19 |  | 75 mm Isolating valve | LI | No | 8
E.1.1.20 |  | 100 mm Isolating valve | LI | No | 1
E.1.1.21 |  | 150 mm Isolating valve | LI | No | 1
E.1.1.22 | PSL 8.2.13 | Anchor/Thrust Blocks | LI | m³ | 5
SUB-TOTAL CARRIED FORWARD
brought forward
E.1.1.23 | PSL 8.2.17 | Soil Crete Casing | LI | m³ | 10
E.1.1.24 | PSLB 8.1.6 | Encasing of Pipes in Concrete (see drawing W74-20/21-BLK-W-D011) | LI | m³ | 10
E.1.1.25 | PSL 8.2.18 | Pipe Markers
|  | Pipe markers shall be installed at 50m intervals on the pipeline route, at all the newly installed isolation and scour valves as indicated on the detailed drawings as well as at all positions where the pipeline route deviates from the horizontal. | LI | No | 380
E.1.1.26 |  | Supply and installation of pre-cast chambers for Water meter and Control Valve Chamber (see drawing W74-20/21-BLK-W-D010) |  | No | 2
E.1.1.27 | PSL 7.3 | STANDARD HYDRAULIC PIPE TEST
E.1.1.28 | PSL 7.3.1 | Test pressure and time of test
Pipes shall not be tested against isolating valves. Special blank flanges or end caps, fully anchored, shall be provided for testing.
TOTAL CARRIED FORWARD TO SUMMARY

## Reticulation
BID NO.: INF-W41/2022/2023 CONSTRUCTION OF BULK WATER SUPPLY IN GROOTPAN, SIAS, LONGDEN GA-RAMASWIKANA (SOUTH CLUSTER) CAPRICORN DISTRICT MUNICIPALITY SCHEDULE OF QUANTITIES SECTION F: RETICULATION
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
| SANS 1200L | SECTION F: MEDIUM PRESSURE PIPELINES
F.1 |  | PIPELINES
F.1.1 | PSL 8.2.1 | Supply, Lay and Bed Pipes complete with couplings
| PSL 8.2.1.1 | Supply, Lay, Joining, Bedding, Testing and Disinfection of uPVC Class 12 Pipes with the following diameters:
F.1.1.1 |  | 75 mm | LI | m | 15700
| PSL 8.2.1.1 | HDPE PE 100 PN12.5 Pipes with the following diameters:
F.1.1.2 |  | 75mm | LI | m | 15700 |  | Rate Only.
F.1.1.3 | PSL 8.2.2 | Extra-over 8.2.1 for the Supplying, Laying, Bedding and Testing of Specials Complete with Couplings
90° elbows:
F.1.1.4 |  | 75 mm | LI | No | 21
45° elbows:
F.1.1.5 |  | 75 mm | LI | No | 9
22,5° elbows:
F.1.1.6 |  | 75 mm | LI | No | 16
11,25° elbows:
F.1.1.7 |  | 75 mm | LI | No | 37
Tees:
F.1.1.8 |  | 75 mm x 75 mm | LI | No | 36
F.1.1.9 |  | 90 mm x 90 mm | LI | No | 1
Reducers:
F.1.1.10 |  | 90 x 75mm | LI | No | 2
F.1.1.11 |  | 200 x 160mm | LI | No | 1
SUB-TOTAL CARRIED FORWARD
brought forward
EndCap:
F.1.1.12 |  | 75 mm dia | LI | No | 6
F.1.1.13 | PSL 8.2.3 | Extra-over 8.2.1 for the Supplying, Laying, Bedding and Testing of Specials Complete with Couplings
| PS L 3.10.1 | Gate valves (see drawing W74-20/21-BLK-W-D008)
F.1.1.14 |  | 75 mm Isolating valve chamber |  | No | 3
F.1.1.15 | PSL 8.2.13 | Anchor/Thrust Blocks |  | m³ | 2
F.1.1.16 | PSL 8.2.13 | Supply and installation of pre-cast valve chambers (complete as per drawing W74-20/21-BLK-W-D005)
F.1.1.17 |  | Gate valve precast chambers (see drawing W74-20/21-BLK-W-D005) |  | No | 20
F.1.1.18 | SANS 1200 LF | Erf Connection
F.1.1.19 | 8.2.1 | Providing erf connections in HDPE pipes and fittings (see drawing W74-20/21-BLK-W-D015)
|  | 32 mm HDPE pipes | LI | No | 370
F.1.1.20 | 8.2.2 | Supply, Lay, Disinfection, Installation and Testing of Erf Connections
|  | The laying of erf connections will be measured on slopes overall as laid | LI | m | 45
F.1.1.21 | 8.2.4 | Supply, install and test meters complete with 25 mm ND couplings (See drawing W74-20/21-BLK-W-D015) | LI | No | 370
F.1.1.22 | 8.2.6 | Supply, install and test brass ball valve (ball-o-stop) complete with special fittings of 25 mm ND (see drawing W74-20/21-BLK-W-D015) | LI | No | 370
F.1.1.23 | 8.2.8 | Markings or marker posts (See drawing W74-20/21-BLK-W-D016) | LI | No | 370
SUB-TOTAL CARRIED FORWARD
brought forward
F.1.1.24 | PSL 7.3 | STANDARD HYDRAULIC PIPE TEST
F.1.1.25 | PSL 7.3.1 | Test pressure and time of test
Pipes shall not be tested against isolating valves. Special blank flanges or end caps, fully anchored, shall be provided for testing.
TOTAL CARRIED FORWARD TO SUMMARY

## Borehole Installation
BID NO.: INF-W41/2022/2023 CONSTRUCTION OF BULK WATER SUPPLY IN GROOTPAN, SIAS, LONGDEN GA-RAMASWIKANA (SOUTH CLUSTER) CAPRICORN DISTRICT MUNICIPALITY SCHEDULE OF QUANTITIES SECTION G: BOREHOLE INSTALLATION
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
SECTION G: BOREHOLE INSTALLATION
G.1 |  | PUMPS
G.1.1 |  | Supply, install and test submersible borehole pumps along with motors at:
G.1.1.1 |  | H11-2774 (Grundfos S30/9, Power: 13kW, Nominal Speed: 2900) |  | No | 1
G.1.1.2 |  | H11-1940 (Grundfos S30/13, Power: 11kW, Nominal Speed: 2900) |  | No | 1
G.1.2 |  | Supply of galvanised pipe-work and HDPE borehole piping including dismantling joint as specified. (Refer to drawing: W74-20/21-BLK-W-D002)
G.1.2.1 |  | H11-2774 (Grundfos S30/9) |  | No | 1
G.1.2.2 |  | H11-1940 (Grundfos S30/13) |  | No | 1
G.1.3 |  | Air Valve (Refer to drawing: W74-20/21-BLK-W-D002)
Double orifice air valve with anti-shock orifice mechanism complete with isolating valve.
G.1.3.1 |  | ND 25 mm |  | No | 2
G.1.4 |  | Pressure Gauge 2500kPa (Refer to drawing: W74-20/21-BLK-W-D002)
G.1.4.1 |  | 50mm ND x 90º HDGMS bend both ends flanged. |  | No | 2
G.1.5 |  | Check Valve (Refer to drawing: W74-20/21-BLK-W-D002)
Supply of flanged swing check valve :
G.1.5.1 |  | ND 50 mm |  | No | 2
G.1.6 |  | Gate Valve (Refer to drawing: W74-20/21-BLK-W-D002)
G.1.6.1 |  | ND 25 mm |  | No | 2
G.1.6.2 |  | ND 50 mm |  | No | 4
SUB-TOTAL CARRIED FORWARD
brought forward
G.1.7 |  | Water Meter
Supply Flanged electromagnetic water meter with reading unit and screen mounted on meter. The meter must be capable of measuring flows of between 0,5 m3/h and 15 m3/h (Refer to drawing: W74-20/21-BLK-W-D002):
G.1.7.1 |  | ND 50 mm |  | No | 2
G.1.8 |  | Flow control valve (Refer to drawing: W74-20/21-BLK-W-D002)
G.1.8.1 |  | ND 50 mm CLA-VAL 40-01 Flow control valve |  | No | 2
G.1.8.2 |  | Orifice plate assembly |  | No | 2
G.1.8.3 |  | Supply of flow switch (threaded) to fit in ND 25 mm connection: |  | No | 2
G.1.9 |  | Electronic working drawing which are to be submitted for approval and used for manufacturing and installation |  | Sum | 1
G.1.10 |  | Supply of all mechanical accessories, including, bolts, nuts and packings
G.1.10.1 |  | H11-2774 (Grundfos S30/9) |  | No | 1
G.1.10.2 |  | H11-1940 (Grundfos S30/13) |  | No | 1
G.1.11 |  | Installation:
G.1.11.1 |  | Installation of all plant and material supplied. Including off-loading, storing until erection, handling, erecting of pump, motor, etc. adjusting, painting, operation, factory testing, site testing and handing over in complete working order, including all electrical gear
|  | H11-2774 (Grundfos S30/9) |  | No | 1
|  | H11-1940 (Grundfos S30/13) |  | No | 1
G.1.12 |  | PC Sum - extension of mechanical pipework |  | PC Sum | 2
SUB-TOTAL CARRIED FORWARD
brought forward
G.1.13 |  | Allow for any additional equipment and/or (Specify): |  | Sum | 2
G.1.14 |  | Supply of flow switch (threaded) to fit in 25 connection (Refer to drawing: W74-20/21-BLK-W-D002) |  | No | 2
G.1.15 |  | Supply, install and test submersible pumps, install all pipework and valves to centrifugal pumps. Pipework to be steel pipe. Valves, non-return valves, meters, etc. to be installed according to manufacturer’s specification. (Refer to drawing: W74-20/21-BLK-W-D002) |  | Sum | 1
G.1.16 |  | Construct pre-cast borehole chamber complete with gantry, ventilators, doors, pipe sleeves, and other necessary specials as indicated on the drawing. (Refer to drawing: W74-20/21-BLK-W-D001) |  | Sum | 1
TOTAL CARRIED FORWARD TO SUMMARY

## Borehole Electricity
BID NO.: INF-W41/2022/2023 CONSTRUCTION OF BULK WATER SUPPLY IN GROOTPAN, SIAS, LONGDEN GA-RAMASWIKANA (SOUTH CLUSTER) CAPRICORN DISTRICT MUNICIPALITY SCHEDULE OF QUANTITIES SECTION H: BOREHOLE ELECTRICITY
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
SECTION H: BOREHOLE ELECTRICITY
H.1 |  | ELECTRICAL MCC's
H.1.1 |  | Supply and installation of new MCC for:
H.1.1.1 |  | H11-2774 (Grundfos S30/9) |  | No | 1
H.1.1.2 |  | H11-1940 (Grundfos S30/13) |  | No | 1
H.1.2 |  | CONTROL EQUIPMENT
Supply, install, connect and test
H.1.2.1 |  | Borehole electrodes |  | No | 2
H.1.2.2 |  | Float level switches |  | No | 2
H.1.2.3 |  | Mechanical Flow Meters (including optosensors)
H.1.2.3.1 |  | H11-2774 (Grundfos S30/9) |  | No | 1
H.1.2.3.2 |  | H11-1940 (Grundfos S30/13) |  | No | 1
H.1.3 |  | GENERAL ELECTRIC WORK
Supply, install and connect
H.1.3.1 |  | Connect MCC supply to:
H.1.3.1.1 |  | H11-2774 (Grundfos S30/9) |  | No | 1
H.1.3.1.2 |  | H11-1940 (Grundfos S30/13) |  | No | 1
H.1.3.2 |  | Sundry equipment such as cable rack, sleeves, cable boxes, brackets, etc |  | Sum | 2
H.1.3.3 |  | Earth mats |  | No | 2
SUB-TOTAL CARRIED FORWARD
brought forward
H.1.4 |  | CABLES
Supply and install
H.1.4.1 |  | Supply Cables: MCC supply: 6 mm² x 4 core + 4 mm²
H.1.4.1.1 |  | H11-2774 (Grundfos S30/9) |  | m | 1460
H.1.4.1.2 |  | H11-1940 (Grundfos S30/13) |  | m | 1220
H.1.4.2 |  | MCC to boreholes for motor cable: 2,5 mm² x 4 core
H.1.4.2.1 |  | H11-2774 (Grundfos S30/9) |  | m | 1460
H.1.4.2.2 |  | H11-1940 (Grundfos S30/13) |  | m | 1220
H.1.4.3 |  | Pressure level sensor cable: 1.5mm² x 3core
H.1.4.3.1 |  | H11-2774 (Grundfos S30/9) |  | No | 1
H.1.4.3.2 |  | H11-1940 (Grundfos S30/13) |  | No | 1
H.1.4.4 |  | Electrode cable: 1.5mm² x 3core
H.1.4.4.1 |  | H11-2774 (Grundfos S30/9) |  | No | 1
H.1.4.4.2 |  | H11-1940 (Grundfos S30/13) |  | No | 1
H.1.4.5 |  | MCC to water meters: 1.5mm² x 3core
H.1.4.5.1 |  | H11-2774 (Grundfos S30/9) |  | m | 1460
H.1.4.5.2 |  | H11-1940 (Grundfos S30/13) |  | m | 1220
H.1.4.6 |  | Outstation from boreholes to reservoir float level switches: 1.5mm² x 3core |  | m | 2600
H.1.4.7 |  | Danger tape |  | m | 5200
H.1.5 |  | CABLE TERMINATION
H.1.5.1 |  | Supply, install and connect cables
H.1.5.1.1 |  | H11-2774 (Grundfos S30/9) |  | No | 1
H.1.5.1.2 |  | H11-1940 (Grundfos S30/13) |  | No | 1
SUB-TOTAL CARRIED FORWARD
brought forward
H.1.5.2 |  | MCC to boreholes
H.1.5.2.1 |  | Motor cable: 2,5 mm² x 4 core |  | sum | 1
H.1.5.2.2 |  | H11-2774 (Grundfos S30/9) |  | No | 1
H.1.5.2.3 |  | H11-1940 (Grundfos S30/13) |  | No | 1
H.1.5.3 |  | Control/Instrumentation:
H.1.5.3.1 |  | Flow meter |  | No | 2
H.1.5.3.2 |  | Pressure Sensor |  | No | 1
H.1.5.3.3 |  | Electrode |  | No | 1
H.1.5.3.4 |  | Limit switch |  | No | 1
H.1.6 |  | TESTING, COMMISSIONING AND HANDING OVER OF EQUIPMENT |  | No | 2
H.1.7 |  | PRELIMINARY AND GENERAL DRAWINGS |  | No | 1
H.1.8 |  | MANUALS |  | No | 2
H.1.9 |  | OTHER EQUIPMENT:
Any item not mentioned above but deemed necessary to provide a fully operational system (Specify)
TOTAL CARRIED FORWARD TO SUMMARY

## Gabions
BID NO.: INF-W41/2022/2023 CONSTRUCTION OF BULK WATER SUPPLY IN GROOTPAN, SIAS, LONGDEN GA-RAMASWIKANA (SOUTH CLUSTER) CAPRICORN DISTRICT MUNICIPALITY SCHEDULE OF QUANTITIES SECTION J: GABIONS
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
| SANS 1200DK | SECTION J: GABIONS AND STONE PITCHING
J.1 |  | GABIONS AND PITCHING
J.1.1 | 8.2.1 | Surface preparation for bedding of gabions
J.1.1.1 | 8.2.1 a) | Cavities filled with approved excavated material or rock | LI | m2 | 500
J.1.2 |  | Reno mattress
Reno mattress formed with a hot dipped galvanized 275mg/m2 coated with 4mm PVC coating (4mm SANS 1580) hexagonal double twist 3mm wire mesh type 60 with 0.08mm tolerance (SANS 675) filled with selected dump rock (without asbestos seams) and tied into adjoining gabions.
J.1.2.1 |  | (a) 1000mm x 500mm x 2000mm | LI | m3 | 210
J.1.2.2 |  | (b) 1000mm x 1000mm x 2000mm | LI | m3 | 210
J.1.4 | 8.2.3 | Extra-over 8.2.2 for packlng selected stone for exposed face | LI | m2 | 550
J.1.5 |  | Geotextile
J.1.5.1 | 8.2.4 | Mactex N20.2 (Non-woven geotextible manufactured with polyester continious filament fibres assebled by a needed punched treatment) | LI | m2 | 2200
J.1.6 | 8.2.5 | Stone pitching | LI | m2 | 680
J.1.7 |  | Erosion control blanket | LI | m2 | 1000
J.1.8 |  | (a) Y12 hot dipped galvanised ground anchor pegs 1.5m in length | LI | No | 150
TOTAL CARRIED FORWARD TO SUMMARY

## Summary
CONTRACT NO. : W41/2022/2023 SCHEDULE OF QUANTITIES SUMMARY OF BILL OF QUANTITIES
Section | Description | Amount
R
A | Preliminary and General
B | Site clearance
C | Earth Works
D | Civil Works-Pipe Work
E | Bulk Pipelines
F | Reticulation
G | Borehole Installation
H | Borehole Electricity
I | Gabions
Subtotal 1
ADD | Contingency @ 10% (Solely for the use of the Client, and only on instruction to Contractor)
ADD | Subtotal 2 VAT @ 15%
TOTAL CARRIED TO FORM OF OFFER
………………………………………………………………….. …………………………………….. SIGNATURE OF TENDERER DATE ………………………………………………………………….. …………………………………….. NAME OF TENDERER DESIGNATION